## Slide 1
D.A.K
Digital Access Key
POC Development Proposal
Scope of POC Completed
A fully functional multi-portal faith-community platform built and deployed with Docker
PLATFORM ARCHITECTURE
Admin Portal (Port 3001)
Platform admin dashboard — approve communities, view GMV, manage users, payment tracking, waiting list management
Institute Portal (Port 3002)
Community admin — manage branding/settings, create events, schedule & run live streams, messaging with members
User Portal (Port 3003)
End user experience — join via invite, community overview with live stream, support widget, upcoming events, calendar, messaging
API Backend (Port 3000)
Node.js/Express REST API with PostgreSQL — JWT auth, role-based access, 16+ API endpoint groups
Docker Compose
Full orchestration of all 5 services (DB, API, Admin, Institute, User) — one-command deployment
KEY FEATURES DELIVERED
Controlled Access — QR/Invite-only onboarding, Chinese-wall isolation across 4 community types
✓
Live Streaming — Embedded player with LIVE badge, viewer count, full playback controls, recording gating
✓
Support & Payments — One-time/Monthly toggle, preset amounts ($16/$36/$100/$250), custom input, 5% platform fee
✓
Events & Calendar — Create/manage events, upcoming events sidebar, mini calendar widget with event dots, ICS export
✓
Private Messaging — Threaded User-Admin inbox, real-time threads, block capability
✓
Community Management — Onboarding, branding settings, member management, stream scheduling & limits
✓
Admin Dashboard — Platform metrics (GMV, users, subscribers), community approval/suspend, payment tracking
✓
Notifications — In-app notification bell with unread count, mark-all-read, event/stream/message alerts
✓
Responsive UI — Apple-inspired design, two-column overview layout, Star of David branding, mobile-ready
✓
D.A.K — Digital Access Key
Slide 1 of 3

## Slide 2
D.A.K
Digital Access Key
POC Development Proposal
Timeline to Build & Demo the POC
4-week sprint plan from kickoff to live demo — single full-stack developer
WEEK 1
Infrastructure & Auth
VPS/Docker environment setup
PostgreSQL schema & seed data
JWT authentication system
OAuth integration (Google/Apple)
Email verification flow
Role-based access control
WEEK 2
Payment & Core Features
Stripe sandbox integration
One-time & recurring payments
Webhook handlers & refunds
Support widget with presets
Platform fee (sliding scale)
Access duration logic
WEEK 3
Features & UI Polish
Live streaming (WebRTC/HLS)
Stream scheduling & limits
Push & email notifications
Calendar & events system
Admin dashboard analytics
UI/UX polish to match mockup
WEEK 4
Testing & Launch
End-to-end integration tests
Security audit & hardening
Load & performance testing
Bug fixes & UAT support
Documentation & handover
Production deployment & demo
KEY MILESTONES
Day 1: Kickoff & environment ready
Week 2: Payment flow end-to-end demo
Week 3: Feature-complete internal review
Week 4: Live demo to stakeholders
D.A.K — Digital Access Key
Slide 2 of 3

## Slide 3
D.A.K
Digital Access Key
POC Development Proposal
Cost Breakdown
Development, infrastructure & operational costs for the POC phase
DEVELOPMENT COST (ONE-TIME)
Week 1: Infrastructure & Auth
$2,500
Week 2: Payment Integration
$2,500
Week 3: Features & Polish
$2,000
Week 4: Testing & Deployment
$1,500
Development Total
$8,500
INFRASTRUCTURE (MONTHLY)
VPS Server (4 vCPU, 8GB)
$40/mo
Domain & SSL
$15/mo
Email Service (SES/SendGrid)
$20/mo
Streaming CDN (basic)
$50/mo
Backups & Monitoring
$25/mo
Monthly Total
$150/mo
THIRD-PARTY SERVICES
Stripe Processing Fee
2.9% + $0.30
OAuth (Google/Apple)
Free
Push Notifications (Firebase)
Free tier
Streaming (usage-based)
~$0.01/min
Variable
Usage-based
TOTAL INVESTMENT SUMMARY
One-Time Development
$8,500
Infrastructure (3 months)
$450
Contingency (10%)
$895
POC Total Investment
$9,845
ASSUMPTIONS & NOTES
Development rate: ~$60/hr (mid-market full-stack rate)
VPS: DigitalOcean/Hetzner tier with Docker pre-installed
Streaming costs scale with usage — estimates for POC testing phase
Excludes: Mobile apps, dedicated support, multi-region deployment
Timeline assumes single developer, can accelerate with team
D.A.K — Digital Access Key
Slide 3 of 3